## Sheet1
		FEB	MAR	APR	MAY	JUNE	JULY	AUG	SEP	OCT	NOV	DEC
Refactor Bluetooth and Wi-Fi Operation		09-FEB		20-APR

Refactor Bluetooth and Wi-fi Operation				21-APR	12-MAY

Fix broken firmware updates (ECG board firmware, battery charger firmware)					13-MAY	22-JUNE

Add support to program and update the TPH firmware						23-JUNE		25-AUG

Refactor External Printer Functionality								26-AUG	15-SEPT

TEST ABOVE UPDATES									16-SEPT	15-OCT