## Sheet1
| FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | DEC
Refactor Bluetooth and Wi-Fi Operation | FEB: 09-FEB; APR: 20-APR
Refactor Bluetooth and Wi-fi Operation | APR: 21-APR; MAY: 12-MAY
Fix broken firmware updates (ECG board firmware, battery charger firmware) | MAY: 13-MAY; JUNE: 22-JUNE
Add support to program and update the TPH firmware | JUNE: 23-JUNE; AUG: 25-AUG
Refactor External Printer Functionality | AUG: 26-AUG; SEP: 15-SEPT
TEST ABOVE UPDATES | SEP: 16-SEPT; OCT: 15-OCT