## Sheet1
Project / Tasks |  | Main resposible | Progess
Variscite PCB Modification And Place Order
Cardipia Variscite | PCB design modified and prepared for production. Some missing lines in the PCB is updated from the reference of manually jumpers soldered in the running board. New gerber file is generated and validated by manufacturer. | Jibon | Order Placed
Holter Solution For Power Consumption During Power Off
Cardicode 300H | Checking and Testing Holter to find a solution for longer battery life during poweroff. | Jibon | 10%
Received the project files
PCB Files | Received and checked the PCB project files for future extensions. | Jibon | 100%
Codes | Received and checked the codes project files of Cardipia 800 Rockchip and older CPU | Jibon | 100%
Porting Mainline Linux Kernel to Rockchip Cardipia
Initiate Porting Main Kernel | Mainline Kernel Is running on Rockchip Processor | Jibon | 100%
Initiate Porting Device Drivers | Start Porting Cardipia Associated Device Drivers | Jibon | 10%